## Slide 1
CLOUDASTA / ACME CUSTOMER PROPOSAL
Acme Field Services
Workspace migration
Migration and administrator enablement
Revision 2.0 · Delivery review pending
Prepared by Cloudasta Delivery
FICTIONAL DEMONSTRATION · 2026-09-05 · FOR REVIEW
01
Notes: Fictional customer proposal. This presentation is not an executed order.

## Slide 2
CLOUDASTA / ACME CUSTOMER PROPOSAL
Operating context
100 mailboxes across a single source tenant
Shared mailboxes require nominated owners
Customer retains control of domain and identity
Target: predictable cutover with reconciled data
FICTIONAL DEMONSTRATION · 2026-09-05 · FOR REVIEW
02
Notes: Acme Field Services wants a managed migration with clear responsibilities. Discovery must confirm mailbox sizes, archive constraints and the customer administrator roster.

## Slide 3
CLOUDASTA / ACME CUSTOMER PROPOSAL
Included services
Discovery workshop and migration plan
One pilot batch and one production cutover
Administrator training and launch coordination
Five working days of migration defect support
FICTIONAL DEMONSTRATION · 2026-09-05 · FOR REVIEW
03
Notes: Migrate 100 mailboxes to the new workspace tenant. The scope includes administrator training and launch coordination. Training covers routine administration and the support escalation route.

## Slide 4
CLOUDASTA / ACME CUSTOMER PROPOSAL
Scope boundaries
Customer owns device and network readiness
Archive export is subject to vendor access
Custom integrations require a change request
No change to contracted incident coverage
FICTIONAL DEMONSTRATION · 2026-09-05 · FOR REVIEW
04
Notes: Excluded: device replacement, historical archive remediation and custom application work. Validate shared mailbox ownership and data handling before the pilot.

## Slide 5
CLOUDASTA / ACME CUSTOMER PROPOSAL
Proposed four-week delivery plan
Week 1: discovery and security approval
Week 2: pilot and reconciliation
Week 3: readiness and administrator training
Week 4: cutover and acceptance
FICTIONAL DEMONSTRATION · 2026-09-05 · FOR REVIEW
05
Notes: Proposed migration delivery window: four weeks after kickoff. Proposal is not a signed contract. The shorter window assumes customer approvals within one working day and a clean pilot. Engineering feasibility remains unconfirmed. The six-week option remains the fallback.

## Slide 6
CLOUDASTA / ACME CUSTOMER PROPOSAL
Readiness and acceptance gates
Approved migration identity and data handling
Complete mailbox and resource-owner roster
Pilot reconciled before production go/no-go
Acceptance pack signed or exceptions assigned
FICTIONAL DEMONSTRATION · 2026-09-05 · FOR REVIEW
06
Notes: Alex Rivera owns delivery readiness. The customer administrator owns access approvals. Customer Success records acceptance and unresolved items with named owners. Do not promise a cutover date before the go/no-go gate.

## Slide 7
CLOUDASTA / ACME CUSTOMER PROPOSAL
Services estimate
Migration services: USD 12,000
One implementation engagement
50% at execution, 50% at acceptance
Subscription fees and taxes excluded
FICTIONAL DEMONSTRATION · 2026-09-05 · FOR REVIEW
07
Notes: Estimated migration services: USD 12000. Final commitments require approval. The estimate excludes recurring subscription charges, taxes, archive remediation and unscoped integrations. Quote validity: 30 calendar days. No accelerated-delivery surcharge has been approved.

## Slide 8
CLOUDASTA / ACME CUSTOMER PROPOSAL
Next steps and approvals
Customer confirms inventory and blackout dates
Delivery validates the proposed window
Finance approves the final quote revision
Both parties execute the order before work starts
FICTIONAL DEMONSTRATION · 2026-09-05 · FOR REVIEW
08
Notes: Commercial owner: Casey Brooks. Delivery owner: Alex Rivera. Customer Success: Riley Foster. The current customer subscription exception remains separate from these project fees. Store the approved proposal and executed order together.